# Software Project Management Plan

## Voice-Controlled Browser Automation Chrome Extension

Project Title: Voice-Controlled Browser Automation Chrome Extension

Uzair Hassan (48525)

Daniyal Wajid (48528)

Semester: Fall 2025

Submission Date: January 13, 2026

Instructor: Adnan Ahmad

University: Riphah International University
Riphah School of Computing & Innovation – Lahore Campus

## PHASE 1: PROJECT INITIATION

### 1.1 Executive Summary

The Voice-Controlled Browser Automation Chrome Extension is an innovative software solution designed to enhance web browsing accessibility and efficiency through natural language voice commands. This project addresses the growing need for hands-free browser interaction, particularly beneficial for users with mobility limitations, multitasking scenarios, and modern accessibility requirements.

The extension leverages the Web Speech API to provide real-time voice recognition and command execution, enabling users to control browser tabs, navigate websites, perform searches, interact with web page elements, and manage bookmarks entirely through voice input. The system incorporates intelligent intent parsing to interpret natural language commands and execute corresponding browser actions seamlessly.

This project demonstrates the practical application of modern web technologies, including Chrome Extension Manifest V3, JavaScript ES6+, and browser automation APIs. The modular architecture ensures maintainability and extensibility, while comprehensive error handling and user feedback mechanisms provide a robust user experience. The project aligns with IEEE 1058-1998 standards for software project management, ensuring systematic planning, execution, and documentation throughout the development lifecycle.

### 1.2 Purpose, Scope, and Objectives

#### Purpose

The primary purpose of this project is to develop a Chrome Extension that enables voice-controlled browser automation, providing users with an intuitive and accessible method to interact with web browsers using natural language voice commands. The extension aims to improve web browsing efficiency, accessibility, and user experience through hands-free operation.

#### Scope

In-Scope: - Voice recognition using Web Speech API - Tab management (open, close, switch, reload) - Website navigation and URL handling - Google and YouTube search functionality - Page scrolling (up/down) - Element interaction (clicking buttons/links) - Window management (minimize/maximize) - Text-to-speech feedback for command confirmation - Error handling and user notifications - Chrome Extension Manifest V3 implementation - Cross-platform compatibility (Windows, macOS, Linux)

Out-of-Scope: - Mobile browser support (Android/iOS) - Offline voice recognition - Multi-language support beyond English - Complex form automation (multi-step workflows) - Browser history management - Download management - Extension settings synchronization across devices - Voice command customization interface

#### Objectives (SMART)

- Specific: Develop a fully functional Chrome Extension with voice recognition capabilities

- Measurable: Complete implementation of all 10 core command categories

- Achievable: Utilize existing Web Speech API and Chrome Extension APIs

- Relevant: Addresses accessibility and efficiency needs

- Time-bound: Complete within 12 weeks

- Specific: Achieve 85% accuracy rate in voice command recognition

- Measurable: Test with 100 sample voice commands across different users

- Achievable: Leverage Web Speech API’s proven recognition capabilities

- Relevant: Ensures reliable user experience

- Time-bound: Validate during testing phase (Week 10-11)

- Specific: Implement modular architecture with separation of concerns

- Measurable: Minimum 5 distinct modules (voiceEngine, intentParser, commandExecutor, etc.)

- Achievable: Follow software engineering best practices

- Relevant: Ensures maintainability and extensibility

- Time-bound: Complete architecture design by Week 3

- Specific: Create comprehensive documentation and user guide

- Measurable: README with installation, usage, and troubleshooting sections

- Achievable: Document as development progresses

- Relevant: Essential for user adoption and maintenance

- Time-bound: Complete documentation by Week 11

- Specific: Ensure zero critical security vulnerabilities

- Measurable: Pass Chrome Web Store security review

- Achievable: Follow Chrome Extension security best practices

- Relevant: Critical for user trust and distribution

- Time-bound: Security audit completed by Week 11

### 1.3 Assumptions and Constraints

#### Assumptions

- Users have access to a functioning microphone and internet connection

- Users are using Chrome browser version 88 or higher (Manifest V3 support)

- Users have basic understanding of voice command syntax

- Web Speech API services are available and accessible

- Target websites are accessible and not blocked by network restrictions

- Users have appropriate permissions granted to the extension

- Development team has access to Chrome Developer Tools and testing environments

- Project stakeholders are available for feedback during review phases

#### Constraints

- Technical Constraints:

- Limited to Chrome/Chromium-based browsers (Edge, Opera)

- Web Speech API requires active internet connection

- Voice recognition accuracy depends on microphone quality and ambient noise

- Chrome Extension Manifest V3 limitations on background scripts

- Content Security Policy restrictions on inline scripts

- Resource Constraints:

- Single developer (student project)

- Limited budget (academic project, no external funding)

- Development time limited to one semester (12-14 weeks)

- No access to paid APIs or cloud services

- Functional Constraints:

- Voice commands must be in English (US locale)

- Cannot execute commands on Chrome internal pages (chrome://)

- Limited to publicly accessible websites

- Cannot bypass website security measures or authentication

- Regulatory Constraints:

- Must comply with Chrome Web Store policies

- Privacy requirements for microphone access

- GDPR considerations for user data handling

### 1.4 Project Deliverables

| S.No |  | Deliverable | Description | Target Date |
| --- | --- | --- | --- | --- |
| 1 | Project Plan | Complete SPM documentation following IEEE 1058-1998 | Week 1 |
| 2 | Requirements Specification | Functional and non-functional requirements document | Week 2 |
| 3 | System Design Document | Architecture, module design, and interface specifications | Week 3 |
| 4 | Source Code | Complete Chrome Extension implementation | Week 4 |
| 5 | Unit & Integration Test | Test cases for all modules | Week 5 |
| 6 | User Documentation | README, installation guide, user manual | Week 6 |
| 7 | Deployment Package | Packaged extension ready for Chrome Web Store | Week 7 |
| 8 | Final Presentation | Project demonstration and presentation | Week 8 |

### 1.5 Feasibility Analysis

#### Technical Feasibility

Analysis: The project is technically feasible based on the following factors:

- Available Technologies:

- Web Speech API (SpeechRecognition) is well-documented and widely supported

- Chrome Extension APIs (tabs, scripting, bookmarks) are mature and stable

- JavaScript ES6+ provides necessary language features

- Chrome Developer Tools enable effective debuggin

- Technical Complexity:

Moderate complexity requiring understanding of:

    - Chrome Extension architecture (Manifest V3)

    - Web Speech API integration

    - Natural language processing basics

    - Browser automation techniques

All technologies are within student capability level

- Risk Assessment:

- Low risk: Technologies are proven and documented

- Medium risk: Voice recognition accuracy may vary

- Mitigation: Implement fallback mechanisms and clear error messages

Conclusion: Technically feasible with available technologies and student expertise level.

#### Economic Feasibility:

Cost Analysis:

| Cost Category | Item | Estimated Cost (PKR) |
| --- | --- | --- |
| Development | Student time (8 weeks @ 14 hrs/week) | 0 (Academic) |
| Tools | Chrome DevTools, VS Code (Free) | 0 |
| Testing | Browser testing, user testing | 0 |
| Hosting | Chrome Web Store (Free) | 0 |
| Documentation | Software licenses (Free tools) | 0 |
| Total Project Cost |  | 0 PKR |

Benefits: - Enhanced browsing accessibility - Improved user productivity - Learning experience for student - Potential for future commercialization - Portfolio project for career development

Conclusion: Highly economically feasible as an academic project with zero monetary investment required.

#### Operational Feasibility

Analysis:

- User Acceptance:

- Voice-controlled interfaces are increasingly popular (Siri, Alexa, Google Assistant)

- Addresses accessibility needs

- Potential high user adoption

- Integration:

- Seamless integration with existing Chrome browser

- No additional software installation required

- Minimal learning curve for users

- Maintenance:

- Modular architecture facilitates easy maintenance

- Chrome Extension updates are straightforward

- Community support available

- Support Requirements:

- Minimal support needed (self-explanatory interface)

- Documentation provides troubleshooting guidance

- User community can provide peer support

Conclusion: Operationally feasible with high user acceptance potential and low maintenance requirements.

#### Schedule Feasibility:

Timeline Analysis:

- Total Duration: 8 weeks

- Available Time: 14 hours per week

- Total Effort: 112 hours

Milestone Breakdown:

Weeks 1-2: Planning & Requirement Analysis (28 hours)

Weeks 3-4: Design & Development (28 hours)

Weeks 5-6: Testing & Documentation (28 hours)

Weeks 7-8: Deployment & Final Review (28 hours)

Critical Path: 1. Requirements → Design → Development → Testing → Deployment

### 1.6 Requirements Specification

#### Functional Requirements

| ID | Requirement | Description | Priority |
| --- | --- | --- | --- |
| FR-001 | Voice Recognition | The system shall recognize voice commands using Web Speech API with continuous listening mode | High |
| FR-002 | Tab Management | The system shall support opening, closing, switching, and reloading browser tabs via voice commands | High |
| FR-003 | Website Navigation | The system shall navigate to specified URLs or common websites using voice commands | High |
| FR-004 | Search Functionality | The system shall perform Google and YouTube searches based on voice input | High |
| FR-005 | Page Scrolling | The system shall scroll web pages up or down based on voice commands | Medium |
| FR-006 | Element Interaction | The system shall click buttons, links, and other interactive elements using voice commands | Medium |
| FR-007 | Bookmark Management | The system shall add and remove bookmarks for the current page using voice commands | Low |
| FR-008 | Window Management | The system shall minimize and maximize browser windows using voice commands | Low |
| FR-009 | Voice Feedback | The system shall provide audio confirmation of executed commands using text-to-speech | High |
| FR-010 | Error Handling | The system shall handle unrecognized commands and provide appropriate error messages | High |
| FR-011 | Start/Stop Control | The system shall provide UI controls to start and stop voice recognition | High |
| FR-012 | Status Indication | The system shall display current listening status (active/inactive) in the popup UI | Medium |
| FR-013 | Intent Parsing | The system shall parse natural language voice commands into structured intents | High |

#### Non-Functional Requirements:

| ID | Category | Metric | Priority |
| --- | --- | --- | --- |
| NFR-001 | Performance | Voice recognition response time < 2 seconds, command execution < 1 second | High |
| NFR-002 | Reliability | System uptime > 99%, error rate < 5% | High |
| NFR-003 | Usability | User can learn basic commands within 5 minutes, intuitive UI design | High |
| NFR-004 | Compatibility | Support Chrome 88+, Edge 88+, Opera 74+ | High |
| NFR-005 | Security | Pass Chrome Web Store security review, no data collection without consent | High |
| NFR-006 | Maintainability | Modular code structure, comprehensive comments, documentation | Medium |
| NFR-007 | Scalability | Architecture supports adding new command types without major refactoring | Low |
| NFR-008 | Accessibility | Voice interface accessible to users with mobility limitations | Medium |
| NFR-009 | Portability | Code structure allows potential porting to other browsers | Low |
| NFR-010 | Efficiency | Minimal memory footprint (< 50MB), CPU usage < 5% during idle | Medium |

## PHASE 2: PROJECT PLANNING

### 2.1 Work Breakdown Structure (WBS)

### 2.2 WBS Dictionary

| WBS ID | Task Name | Description | Deliverable | Predecessor | Days | Resources |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1.1 | Requirements Gathering | Collect and document functional and non-functional requirements | Requirements Document | - | 5 | Developer |
| 1.1.2 | Feasibility Study | Analyze technical, economic, operational, and schedule feasibility | Feasibility Report | 1.1.1 | 3 | Developer |
| 1.1.3 | Project Plan Documentation | Create comprehensive project plan following IEEE 1058-1998 | Project Plan Document | 1.1.2 | 7 | Developer |
| 1.1.4 | Risk Assessment | Identify and analyze project risks | Risk Register | 1.1.2 | 2 | Developer |
| 1.2.1 | Architecture Design | Design system architecture and component structure | Architecture Document | 1.1.3 | 5 | Developer |
| 1.2.2 | Module Design | Design individual modules and their interfaces | Module Design Document | 1.2.1 | 4 | Developer |
| 1.2.3 | Interface Design | Design UI/UX for popup interface | UI Mockups | 1.2.1 | 3 | Developer |
| 1.3.1 | Environment Setup | Set up development environment and tools | Configured Environment | 1.2.2 | 2 | Developer |
| 1.3.2.1 | Voice Engine Module | Implement voice recognition and TTS functionality | voiceEngine.js | 1.3.1 | 5 | Developer |
| 1.3.2.2 | Intent Parser Module | Implement natural language parsing | intentParser.js | 1.3.1 | 6 | Developer |
| 1.3.2.3 | Command Executor Module | Implement command execution logic | commandExecutor.js | 1.3.2.2 | 4 | Developer |
| 1.3.2.4 | Utility Modules | Implement helper functions and utilities | utils/helpers.js | 1.3.1 | 2 | Developer |
| 1.3.3.1 | Manifest Configuration | Create and configure manifest.json | manifest.json | 1.2.2 | 1 | Developer |
| 1.3.3.2 | Popup UI | Develop popup HTML, CSS, and JavaScript | popup.html/css/js | 1.2.3 | 5 | Developer |
| 1.3.3.3 | Background Service Worker | Implement background script for command execution | background.js | 1.3.2.3 | 6 | Developer |
| 1.3.3.4 | Content Scripts | Implement content script for page interaction | contentScript.js | 1.3.2.1 | 4 | Developer |
| 1.3.4.1 | Module Integration | Integrate all modules together | Integrated Codebase | 1.3.3.4 | 3 | Developer |
| 1.3.4.2 | API Integration | Integrate Chrome Extension APIs | Working Extension | 1.3.4.1 | 2 | Developer |
| 1.3.4.3 | Cross-component Communication | Implement message passing between components | Communication System | 1.3.4.2 | 2 | Developer |
| 1.4.1 | Unit Testing | Write and execute unit tests for each module | Unit Test Suite | 1.3.4.3 | 5 | Developer |
| 1.4.2 | Integration Testing | Test integrated components | Integration Test Results | 1.4.1 | 4 | Developer |
| 1.4.3 | System Testing | End-to-end system testing | System Test Report | 1.4.2 | 5 | Developer |
| 1.4.4 | User Acceptance Testing | Conduct UAT with sample users | UAT Report | 1.4.3 | 3 | Developer, Users |
| 1.4.5 | Bug Fixing | Fix identified bugs and issues | Bug Fix Report | 1.4.4 | 4 | Developer |
| 1.5.1 | Technical Documentation | Document technical architecture and code | Technical Docs | 1.4.5 | 3 | Developer |
| 1.5.2 | User Documentation | Create user guide and README | User Manual | 1.4.5 | 3 | Developer |
| 1.5.3 | API Documentation | Document APIs and interfaces | API Docs | 1.5.1 | 2 | Developer |
| 1.5.4 | Installation Guide | Create installation and setup guide | Installation Guide | 1.5.2 | 1 | Developer |
| 1.6.1 | Extension Packaging | Package extension for distribution | .crx/.zip Package | 1.5.4 | 1 | Developer |
| 1.6.2 | Chrome Web Store Preparation | Prepare store listing and assets | Store Listing | 1.6.1 | 2 | Developer |
| 1.6.3 | Submission Process | Submit extension to Chrome Web Store | Submitted Extension | 1.6.2 | 1 | Developer |
| 1.6.4 | Post-Deployment Support | Monitor and address post-deployment issues | Support Log | 1.6.3 | Ongoing | Developer |

## 2.2 Effort Estimation

## 2.2.1 Selected Estimation Technique

## Technique Used: COCOMO I – Basic Model
Tool Used: Manual COCOMO Calculation

## 2.2.2 COCOMO Estimation

| ## Parameter | ## Value |
| --- | --- |
| ## Project Type | ## Organic |
| ## Estimated KLOC | ## 3.05 KLOC |
| ## Effort (Person-Months) | ## 7.68 |
| ## Development Time (Months) | ## 5.38 |
| ## Team Size | ## 1 |

## 2.3 Cost Estimation

| Resource / Item | Quantity | Rate (PKR) | Total Cost (PKR) |
| --- | --- | --- | --- |
| Software Developer | 2 Person-Months | 80,000 / month | 160,000 |
| QA / Testing Engineer | 2 Person-Months | 50,000 / month | 100,000 |
| Project Management & Coordination | Included | — | 0 |
| Testing Tools & User Evaluation | Included | — | 0 |
| Development Tools & IDEs | — | Free / Open Source | 0 |
| APIs & Browser Services | — | Free | 0 |
| Infrastructure (Hardware, Internet, Power) | — | Existing | 0 |
| Documentation & Training Material | Included | — | 0 |
| Subtotal (Development Cost) |  |  | 260,000 |

## PHASE 3: PROJECT SCHEDULING

### 3.1 Activity List

| ID | Activity Name | Duration (Days) | Predecessors | Resources | WBS Ref |
| --- | --- | --- | --- | --- | --- |
| A1 | Project Planning | 3 | – | Developer | 1.1.3 |
| A2 | Requirements Gathering | 3 | A1 | Developer | 1.1.1 |
| A3 | Feasibility Study | 2 | A2 | Developer | 1.1.2 |
| A4 | Risk Assessment | 2 | A3 | Developer | 1.1.4 |
| A5 | Architecture Design | 3 | A3 | Developer | 1.2.1 |
| A6 | Module Design | 2 | A5 | Developer | 1.2.2 |
| A7 | Interface Design | 2 | A5 | Developer | 1.2.3 |
| A8 | Environment Setup | 2 | A6 | Developer | 1.3.1 |
| A9 | Voice Engine Development | 3 | A8 | Developer | 1.3.2.1 |
| A10 | Intent Parser Development | 3 | A8 | Developer | 1.3.2.2 |
| A11 | Command Executor Development | 2 | A10 | Developer | 1.3.2.3 |
| A12 | Utility Modules Development | 2 | A8 | Developer | 1.3.2.4 |
| A13 | Manifest Configuration | 1 | A6 | Developer | 1.3.3.1 |
| A14 | Popup UI Development | 3 | A7 | Developer | 1.3.3.2 |
| A15 | Background Service Worker | 3 | A11 | Developer | 1.3.3.3 |
| A16 | Content Scripts Development | 3 | A9 | Developer | 1.3.3.4 |
| A17 | Module Integration | 2 | A15, A16 | Developer | 1.3.4.1 |
| A18 | API Integration | 2 | A17 | Developer | 1.3.4.2 |
| A19 | Cross-component Communication | 1 | A18 | Developer | 1.3.4.3 |
| A20 | Unit Testing | 3 | A19 | Developer | 1.4.1 |
| A21 | Integration Testing | 2 | A20 | Developer | 1.4.2 |
| A22 | System Testing | 2 | A21 | Developer | 1.4.3 |
| A23 | User Acceptance Testing | 2 | A22 | Developer, Users | 1.4.4 |
| A24 | Bug Fixing | 2 | A23 | Developer | 1.4.5 |
| A25 | Technical Documentation | 2 | A24 | Developer | 1.5.1 |
| A26 | User Documentation | 2 | A24 | Developer | 1.5.2 |
| A27 | API Documentation | 1 | A25 | Developer | 1.5.3 |
| A28 | Installation Guide | 1 | A26 | Developer | 1.5.4 |
| A29 | Extension Packaging | 1 | A28 | Developer | 1.6.1 |
| A30 | Chrome Web Store Preparation | 2 | A29 | Developer | 1.6.2 |
| A31 | Final Presentation & Submission | 2 | A30 | Developer | 1.6.3 |

### 3.2 Gantt Chart

Description: The Gantt chart represents project activities over a 56-day timeline. Tasks are shown as horizontal bars with dependencies illustrated through arrows. The critical path is highlighted to show activities that directly affect the project completion date.

3.3 Critical Path Method (CPM) Analysis:

3.3.1 Network Diagram:

3.3.2 Forward Pass Calculation:

| Activity | Duration | ES (Early Start) | EF (Early Finish) | Calculation |
| --- | --- | --- | --- | --- |
| A1 | 3 | 0 | 3 | 0 + 3 |
| A2 | 3 | 3 | 6 | EF(A1) + 3 |
| A3 | 2 | 6 | 8 | EF(A2) + 2 |
| A5 | 3 | 8 | 11 | EF(A3) + 3 |
| A6 | 2 | 11 | 13 | EF(A5) + 2 |
| A8 | 2 | 13 | 15 | EF(A6) + 2 |
| A10 | 3 | 15 | 18 | EF(A8) + 3 |
| A11 | 2 | 18 | 20 | EF(A10) + 2 |
| A15 | 3 | 20 | 23 | EF(A11) + 3 |
| A17 | 2 | 23 | 25 | EF(A15) + 2 |
| A18 | 2 | 25 | 27 | EF(A17) + 2 |
| A19 | 1 | 27 | 28 | EF(A18) + 1 |
| A20 | 3 | 28 | 31 | EF(A19) + 3 |
| A21 | 2 | 31 | 33 | EF(A20) + 2 |
| A22 | 2 | 33 | 35 | EF(A21) + 2 |
| A23 | 2 | 35 | 37 | EF(A22) + 2 |
| A24 | 2 | 37 | 39 | EF(A23) + 2 |
| A26 | 2 | 39 | 41 | EF(A24) + 2 |
| A28 | 1 | 41 | 42 | EF(A26) + 1 |
| A29 | 1 | 42 | 43 | EF(A28) + 1 |
| A30 | 2 | 43 | 45 | EF(A29) + 2 |
| A31 | 2 | 45 | 47 | EF(A30) + 2 |

3.3.3 Backward Pass Calculation

| Activity | Duration | LS (Late Start) | LF (Late Finish) | Calculation |
| --- | --- | --- | --- | --- |
| A31 | 2 | 54 | 56 | 56 − 2 |
| A30 | 2 | 52 | 54 | 54 − 2 |
| A29 | 1 | 51 | 52 | 52 − 1 |
| A28 | 1 | 50 | 51 | 51 − 1 |
| A26 | 2 | 48 | 50 | 50 − 2 |
| A24 | 2 | 46 | 48 | 48 − 2 |
| A23 | 2 | 44 | 46 | 46 − 2 |
| A22 | 2 | 42 | 44 | 44 − 2 |
| A21 | 2 | 40 | 42 | 42 − 2 |
| A20 | 3 | 37 | 40 | 40 − 3 |
| A19 | 1 | 36 | 37 | 37 − 1 |
| A18 | 2 | 34 | 36 | 36 − 2 |
| A17 | 2 | 32 | 34 | 34 − 2 |
| A15 | 3 | 29 | 32 | 32 − 3 |
| A11 | 2 | 27 | 29 | 29 − 2 |
| A10 | 3 | 24 | 27 | 27 − 3 |
| A8 | 2 | 22 | 24 | 24 − 2 |
| A6 | 2 | 20 | 22 | 22 − 2 |
| A5 | 3 | 17 | 20 | 20 − 3 |
| A3 | 2 | 15 | 17 | 17 − 2 |
| A2 | 3 | 12 | 15 | 15 − 3 |
| A1 | 3 | 9 | 12 | 12 − 3 |

3.3.4 Slack Time Calculation

| Activity | ES | EF | LS | LF | Slack (LS − ES) | Critical? |
| --- | --- | --- | --- | --- | --- | --- |
| A1 | 0 | 3 | 0 | 3 | 0 | Yes |
| A2 | 3 | 6 | 3 | 6 | 0 | Yes |
| A3 | 6 | 8 | 6 | 8 | 0 | Yes |
| A5 | 8 | 11 | 8 | 11 | 0 | Yes |
| A6 | 11 | 13 | 11 | 13 | 0 | Yes |
| A8 | 13 | 15 | 13 | 15 | 0 | Yes |
| A10 | 15 | 18 | 15 | 18 | 0 | Yes |
| A11 | 18 | 20 | 18 | 20 | 0 | Yes |
| A15 | 20 | 23 | 20 | 23 | 0 | Yes |
| A17 | 23 | 25 | 23 | 25 | 0 | Yes |
| A18 | 25 | 27 | 25 | 27 | 0 | Yes |
| A19 | 27 | 28 | 27 | 28 | 0 | Yes |
| A20 | 28 | 31 | 28 | 31 | 0 | Yes |
| A21 | 31 | 33 | 31 | 33 | 0 | Yes |
| A22 | 33 | 35 | 33 | 35 | 0 | Yes |
| A23 | 35 | 37 | 35 | 37 | 0 | Yes |
| A24 | 37 | 39 | 37 | 39 | 0 | Yes |
| A26 | 39 | 41 | 39 | 41 | 0 | Yes |
| A28 | 41 | 42 | 41 | 42 | 0 | Yes |
| A29 | 42 | 43 | 42 | 43 | 0 | Yes |
| A30 | 43 | 45 | 43 | 45 | 0 | Yes |
| A31 | 45 | 47 | 45 | 47 | 0 | Yes |

3.3.5 Critical Path

Critical Path:
A1 → A2 → A3 → A5 → A6 → A8 → A10 → A11 → A15 → A17 → A18 → A19 → A20 → A21 → A22 → A23 → A24 → A26 → A28 → A29 → A30 → A31

Total Project Duration: 56 Days

3.4 Project Calendar / Timeline

| Phase / Milestone | Start Date | End Date | Duration |
| --- | --- | --- | --- |
| Phase 1: Planning & Analysis | Day 1 | Day 8 | 8 Days |
| Phase 2: Design | Day 9 | Day 15 | 7 Days |
| Phase 3: Development | Day 16 | Day 35 | 20 Days |
| Phase 4: Testing | Day 36 | Day 47 | 12 Days |
| Phase 5: Deployment & Documentation | Day 48 | Day 56 | 9 Days |
| Project Completion | Day 1 | Day 56 | 56 Days |

## PHASE 4: PROJECT EXECUTION & CONTROL

### 4.1 Communication Plan

4.1.1 Stakeholder Communication Matrix

| Stakeholder | Information Needs | Frequency | Method | Responsible |
| --- | --- | --- | --- | --- |
| Instructor | Progress updates, guidance | Weekly | Email, Meetings | Developer |
| Project Supervisor | Technical review, feedback | Bi-weekly | Email, Meetings | Developer |
| End Users (Testing) | Feedback during UAT | During UAT | Surveys, Interviews | Developer |
| Development Team | Status updates, blockers | Daily (if team) | Daily Standups | Developer |
| University Administration | Academic compliance reports | Monthly | Formal Reports | Developer |

Communication Channels:

- Email: Primary formal communication

- Meetings: Weekly progress reviews

- Documentation: Project repository (GitHub)

- Presentations: Mid-term and final presentations

Communication Protocols:

- Response time: 24–48 hours for emails

- Meeting minutes: Documented and shared

- Status reports: Weekly written updates

- Escalation: Issues reported within 24 hours

### 4.1.2 RACI Matrix

(R = Responsible, A = Accountable, C = Consulted, I = Informed)

| Activity / Deliverable | PM (Developer) | Developer | Tester | Client (Users) | Sponsor (Instructor) |
| --- | --- | --- | --- | --- | --- |
| Requirements Gathering | A | R | C | I | C |
| System Design | A | R | – | – | C |
| Development | A | R | – | – | I |
| Unit Testing | A | R | – | – | I |
| Integration Testing | A | R | – | – | C |
| System Testing | A | R | – | I | C |
| User Acceptance Testing | R | C | – | A | C |
| Documentation | A | R | – | – | C |
| Deployment | A | R | – | – | C |
| Bug Fixing | A | R | – | I | I |

### 4.2 Staffing Plan

### 4.2.1 Team Structure

The project follows a single-developer academic team structure.
All roles including Project Manager, Developer, Tester, and Technical Writer are performed by the student developer, under the supervision of the instructor and project supervisor. External users participate only during the User Acceptance Testing phase.

4.2.2 Resource Allocation

| Role | Name/ID | Allocation % | Skills Required | Duration |
| --- | --- | --- | --- | --- |
| Project Manager | Developer (Student) | 100% | Project management, communication | Full Project |
| Developer | Developer (Student) | 100% | JavaScript, Chrome APIs, Web Speech API | Weeks 1–8 |
| Tester | Developer (Student) | 30% | Testing methodologies, QA | Weeks 6–7 |
| Technical Writer | Developer (Student) | 20% | Technical writing, documentation tools | Weeks 7–8 |
| User Tester | External Users | 10% | Basic computer skills | UAT Phase |

## 4.3 Risk Management Plan

### 4.3.1 Risk Register

| ID | Risk Description | Probability | Impact | Priority | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- |
| R1 | Web Speech API unavailable or unreliable | Medium | High | High | Test API early, implement fallback mechanisms |
| R2 | Voice recognition accuracy below threshold | Medium | High | High | Command confirmation and improved parsing |
| R3 | Chrome API changes | Low | High | Medium | Monitor release notes, use stable APIs |
| R4 | Insufficient development time | Medium | High | High | Prioritize core features, agile planning |
| R5 | Academic workload conflicts | High | Medium | Medium | Buffer time, task prioritization |
| R6 | Browser compatibility issues | Medium | Medium | Medium | Early multi-browser testing |
| R7 | Security vulnerabilities | Low | High | High | Follow security best practices |
| R8 | Low user adoption | Low | Low | Low | Improve UX and documentation |

4.3.2 Risk Matrix

| Probability / Impact | Low Impact | Medium Impact | High Impact |
| --- | --- | --- | --- |
| High Probability | R5 (Academic workload conflicts) | R4 (Insufficient development time) | R1 (Web Speech API issues) |
| Medium Probability | R8 (Low user adoption) | R2 (Voice recognition accuracy), R6 (Browser compatibility), R10 (Post-deployment bugs), R11 (Microphone permission issues), R12 (Performance issues) | R7 (Security vulnerabilities) |
| Low Probability | R8 (Low user adoption) | R3 (Chrome API changes), R9 (Extension rejection) | — |

### Risk Priority Interpretation

- High Risk (Red Zone):
Risks with High Impact and Medium/High Probability
Immediate monitoring and mitigation required
(R1, R2, R4, R7)

- Medium Risk (Yellow Zone):
Risks with Medium Impact or Probability
Regular monitoring
(R3, R5, R6, R9, R10, R11, R12)

- Low Risk (Green Zone):
Risks with Low Impact and Low Probability
Minimal monitoring
(R8)

## 4.4 Quality Plan

### 4.4.1 Quality Objectives

- Code coverage ≥ 80%

- Code follows JavaScript best practices (ESLint)

- All functional requirements implemented (100%)

- Voice recognition accuracy ≥ 85%

- Command execution success rate ≥ 90%

- Response time < 2 seconds

- User satisfaction ≥ 4/5

4.4.2 Quality Assurance Activities

| Activity | Description | Frequency | Responsible |
| --- | --- | --- | --- |
| Requirements Review | Validate requirements completeness | Once | Developer, Instructor |
| Design Review | Inspect system architecture | Once | Developer, Supervisor |
| Code Review | Review code for standards | Each module | Developer |
| Unit Testing | Test individual components | Continuous | Developer |
| Integration Testing | Test module interactions | Weekly | Developer |
| System Testing | Verify system requirements | Once | Developer |
| User Acceptance Testing | Validate user satisfaction | Once | Developer, Users |
| Final Review | Ensure readiness for deployment | Once | Developer, Instructor |

## 4.5 Procurement Plan

### 4.5.1 Procurement Items

| Item / Service | Vendor / Source | Estimated Cost (PKR) | Procurement Date / Phase |
| --- | --- | --- | --- |
| Development Tools | Visual Studio Code, Chrome DevTools | 0 (Free / Open Source) | Environment Setup Phase |
| Version Control System | GitHub (Free Tier) | 0 (Free) | Environment Setup Phase |
| Testing Tools | Chrome Browser, Built-in DevTools, Manual Testing | 0 (Free) | Testing Phase |
| Documentation Tools | Markdown Editors, MS Word / Google Docs | 0 (Free) | Documentation Phase |
| Hosting & Deployment | Chrome Web Store (Developer Console) | 0 (Free) | Deployment Phase |

Procurement Notes:

- All tools and services are freely available

- No external vendors required

- No formal procurement process needed

## PHASE 5: PROJECT TOOLS & METHODOLOGIES

### 5.1 Taiga Usage

Tool: Taiga.io (Project Management)

Purpose: Taiga is used for agile project management, tracking user stories, tasks, sprints, and project progress.

Usage Description:

- Project Creation:

  - Created project: “Voice-Controlled Browser Automation Chrome Extension”

  - Set up project template: Scrum/Kanban hybrid

  - Configured project settings and team members

- User Stories Creation:

  - Created epics for major features (Voice Recognition, Tab Management, Navigation, etc.)

  - Broke down epics into user stories

  - Example: “As a user, I want to open new tabs using voice commands so that I can browse hands-free”

- Sprint Planning:

  - Organized work into 2-week sprints

  - Assigned user stories to sprints based on priority

  - Estimated story points using planning poker

- Task Management:

  - Created tasks for each user story

  - Assigned tasks to developer

  - Set task statuses: New, In Progress, Ready for Testing, Done

- Progress Tracking:

  - Updated task statuses daily

  - Used burndown charts to track sprint progress

  - Generated velocity reports

- Backlog Management:

  - Maintained product backlog with prioritized features

  - Refined backlog items during sprint planning

  - Moved completed items to “Done” status

Benefits: - Visual progress tracking - Better task organization - Improved time management - Clear visibility of project status

### 5.2 GitHub Repository Usage

Repository: github.com/[username]/voice-agent-extension

Purpose: Version control, code collaboration, issue tracking, and project documentation.

Usage Description:

- Repository Setup:

  - Created repository with README.md

  - Initialized with .gitignore for Node.js/Chrome Extensions

  - Set up branch protection rules

- Branch Strategy:

  - main: Production-ready code

  - develop: Integration branch for features

  - feature/*: Feature development branches

  - bugfix/*: Bug fix branches

  - hotfix/*: Critical production fixes

- Commit Practices:

  - Descriptive commit messages following conventional commits

  - Regular commits (at least daily)

  - Atomic commits (one logical change per commit)

- Pull Request Process:

  - Create feature branch from develop

  - Develop and test feature

  - Create pull request to develop

  - Code review (self-review for solo project)

  - Merge after approval

- Issue Tracking:

  - Created issues for bugs, features, and tasks

  - Used labels: bug, enhancement, documentation, question

  - Linked issues to pull requests

  - Closed issues when resolved

- Releases:

  - Tagged releases (v1.0.0, v1.1.0, etc.)

  - Created release notes

  - Attached extension packages to releases

Repository Structure:

voice-agent-extension/
├── .github/
│   └── workflows/     # CI/CD workflows
├── docs/              # Documentation
├── src/               # Source code
├── tests/             # Test files
├── .gitignore
├── README.md
└── LICENSE

### 5.3 Branch Strategy

Git Flow Model:

- main Branch:

  - Contains production-ready code

  - Protected branch (no direct commits)

  - Only merged from develop or hotfix branches

  - Tagged with version numbers

- develop Branch:

  - Integration branch for completed features

  - Always in deployable state

  - Merged to main for releases

- Feature Branches:

  - Naming: feature/voice-engine, feature/tab-management

  - Created from develop

  - Merged back to develop when complete

  - Deleted after merge

- Bugfix Branches:

  - Naming: bugfix/voice-recognition-error

  - Created from develop

  - Merged to develop and main

  - Deleted after merge

- Hotfix Branches:

  - Naming: hotfix/security-patch

  - Created from main

  - Merged to main and develop

  - Deleted after merge

Branch Workflow Example:

1. Create feature branch: git checkout -b feature/voice-engine develop
2. Develop feature, commit changes
3. Push branch: git push origin feature/voice-engine
4. Create pull request to develop
5. Review and merge
6. Delete feature branch

### 5.4 Tool Usage Table

| Tool Category | Tool Name | Purpose | Usage Frequency | Cost |
| --- | --- | --- | --- | --- |
| IDE / Editor | Visual Studio Code | Code development & debugging | Daily | Free |
| Version Control | Git | Source code management | Daily | Free |
| Repository Hosting | GitHub | Collaboration & code hosting | Daily | Free |
| Project Management | Taiga | Sprint & task management | Daily | Free |
| Browser | Google Chrome | Development & testing | Daily | Free |
| Debugging | Chrome DevTools | Extension debugging | Daily | Free |
| Testing | Chrome Extension Test Framework | Automated testing | Weekly | Free |
| Documentation | Markdown | Technical & user documentation | Weekly | Free |
| UI Design | Figma (Optional) | UI mockups | As needed | Free |
| Communication | Email | Stakeholder communication | Daily | Free |
| Code Quality | ESLint | Code linting & standards | Daily | Free |
| Package Management | npm (Optional) | Dependency management | As needed | Free |
| API Testing | Postman (Optional) | API validation | As needed | Free |
| Screen Recording | OBS Studio | Demo & presentation videos | As needed | Free |

### Tool Integration

- VS Code integrated with Git for version control

- Chrome DevTools used for extension debugging

- GitHub Actions utilized for CI/CD (if implemented)

- ESLint integrated within IDE for code quality enforcement

## APPENDICES

### Appendix A: Glossary

| Term | Definition |
| --- | --- |
| Chrome Extension | A software program that extends the functionality of the Google Chrome browser |
| Manifest V3 | The third version of Chrome Extension manifest specification |
| Web Speech API | Browser API that provides speech recognition and synthesis capabilities |
| Service Worker | Background script that runs independently of web pages in Manifest V3 |
| Content Script | JavaScript code that runs in the context of web pages |
| Intent Parsing | Process of converting natural language into structured command representations |
| CPM | Critical Path Method - project scheduling technique |
| WBS | Work Breakdown Structure - hierarchical decomposition of project work |
| COCOMO | Constructive Cost Model - software cost estimation model |
| RACI | Responsibility Assignment Matrix (Responsible, Accountable, Consulted, Informed) |
| UAT | User Acceptance Testing - final testing phase with end users |
| TTS | Text-to-Speech - conversion of text to spoken audio |
| STT | Speech-to-Text - conversion of speech to text |
| API | Application Programming Interface - set of protocols for building software |
| CRX | Chrome Extension package file format |
| CSP | Content Security Policy - security standard for preventing XSS attacks |
| MVP | Minimum Viable Product - version with minimum features for release |
| Agile | Iterative software development methodology |
| Scrum | Agile framework for managing product development |
| Kanban | Visual workflow management method |
| Burndown Chart | Graphical representation of work remaining over time |
| Velocity | Measure of work completed per sprint in agile development |
| Pull Request | Proposed changes to a codebase submitted for review |
| Commit | Snapshot of changes in version control |
| Branch | Parallel version of codebase for isolated development |
| Merge | Combining changes from different branches |
| Hotfix | Urgent fix applied directly to production code |
| Feature Branch | Branch created for developing a specific feature |
| IEEE 1058-1998 | IEEE standard for software project management plans |

### Appendix B: References

- IEEE Computer Society. (1998). IEEE Std 1058-1998 - IEEE Standard for Software Project Management Plans. New York, NY: IEEE.

- Google Developers. (2023). Chrome Extension Documentation. Retrieved from https://developer.chrome.com/docs/extensions/

- Mozilla Developer Network. (2023). Web Speech API. Retrieved from https://developer.mozilla.org/en-US/docs/Web/API/Web_Speech_API

- W3C. (2023). Web Speech API Specification. Retrieved from https://wicg.github.io/speech-api/

- Boehm, B. W. (1981). Software Engineering Economics. Englewood Cliffs, NJ: Prentice-Hall.

- Project Management Institute. (2017). A Guide to the Project Management Body of Knowledge (PMBOK Guide) (6th ed.). Newtown Square, PA: PMI.

- Chrome Web Store. (2023). Chrome Web Store Developer Dashboard. Retrieved from https://chrome.google.com/webstore/devconsole

- GitHub. (2023). Git Documentation. Retrieved from https://git-scm.com/doc

- Taiga.io. (2023). Taiga Project Management Documentation. Retrieved from https://docs.taiga.io/

- Stack Overflow. (2023). Chrome Extension Development Community. Retrieved from https://stackoverflow.com/questions/tagged/google-chrome-extension

- Chrome Developers. (2023). Manifest V3 Migration Guide. Retrieved from https://developer.chrome.com/docs/extensions/mv3/intro/

- W3Schools. (2023). JavaScript Tutorial. Retrieved from https://www.w3schools.com/js/

- MDN Web Docs. (2023). JavaScript Guide. Retrieved from https://developer.mozilla.org/en-US/docs/Web/JavaScript/Guide

- Google Developers. (2023). Chrome Extension APIs Reference. Retrieved from https://developer.chrome.com/docs/extensions/reference/

- Riphah International University. (2025). Software Project Management Course Syllabus. Lahore, Pakistan: Riphah School of Computing & Innovation.

### Appendix C: Tool Screenshots

#### C.1 Taiga Project Management Screenshot

Description: This screenshot shows the Taiga project dashboard displaying: - Project overview with progress indicators - Active sprints and their burndown charts - User stories organized by epic - Task board showing tasks in different status columns (New, In Progress, Ready for Testing, Done) - Team velocity chart - Recent activity feed

Key Elements Visible: - Sprint backlog with prioritized user stories - Task assignments and due dates - Progress percentage for current sprint - Completed vs. remaining story points

#### C.2 GitHub Repository Screenshot

Description: This screenshot displays the GitHub repository for the Voice Agent Extension showing: - Repository name and description - Branch selector (showing main/develop branches) - File structure in the repository - README.md content preview - Commit history with recent commits - Issues and pull requests tabs - Contributors section - Release tags

Key Elements Visible: - Source code files organized in directories - Commit messages following conventional commit format - Branch protection rules indicator - Repository statistics (commits, branches, releases)

#### C.3 Chrome Extension Developer Dashboard Screenshot

Description: This screenshot shows the Chrome Web Store Developer Dashboard displaying: - Extension listing information - Version history and release notes - Statistics (users, ratings, reviews) - Store listing details (description, screenshots, icons) - Privacy practices and permissions - Publishing status

Key Elements Visible: - Extension package upload interface - Store listing preview - Analytics dashboard - User feedback and reviews section

#### C.4 VS Code Development Environment Screenshot

Description: This screenshot shows the Visual Studio Code editor with: - Open source files (manifest.json, popup.js, background.js) - File explorer sidebar - Integrated terminal - Chrome Extension debugging panel - Code editor with syntax highlighting - Git integration showing file changes

Key Elements Visible: - Project file structure - Code editor with multiple tabs - Debugging breakpoints - Extension output/logs - Git status indicators

#### C.5 Chrome Extension Popup Screenshot

Description: This screenshot shows the extension popup UI displaying: - Extension name and logo - Status indicator (Listening/Inactive) - Start/Stop voice control buttons - Voice command examples list - Transcript display area showing recent commands - Visual feedback for active listening state

Key Elements Visible: - Modern, clean UI design - Status indicators with color coding - Command examples for user guidance - Real-time transcript updates

## Document Control

Document Version: 1.0
Last Updated: December 15, 2024
Author: Daniyal Wajid
Reviewer: Adnan Ahmad
Approval Status: Pending

Revision History:

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | December 15, 2024 | Daniyal Wajid | Initial document creation |

END OF DOCUMENT